## Sheet0
ID | Project ID | Project Name | Key ID | Key | Issue Type ID | Issue Type | Version ID | Version | Subject | Description | Status ID | Status | Priority | Resolution ID | Resolution | Create User ID | Created by | Created Date | Update User ID | Updated by | Updated | Attachment | Shared File | Comment1 | Comment2
3651534 | 68233 | ATM Project | 7 | ATM_1-7 | 292240 | Bug | 63979 | 1.1 | MFT - Incorrect dispensed amounts | Multiple Issues with correct amounts being recognized during withdrawals. Errors are with different amounts and include non-matching dispensed amounts, non-matching account balance reductions, or even both. Function: Withdrawing money as a customer Initial state: System is on and displaying multiples of 20 dollars for customer to withdraw Steps to reproduce: Turn ATM on, enter a valid amount of money, log into an account. Press 1 to choose Withdrawal. Choose an account to withdraw money from (eg. Press 1 for checking). Choose a valid amount of money to be withdrawn (eg. Press 1 to withdraw $20) Expected outcome: Correct amount of cash is withdrawn from the account Actual outcome: Incorrect amount of cash is withdrawn. The receipt and balance are updated with amount that was dispensed. Eg. Upon selection of $20 withdrawal, $40 is dispensed and account balance is updated with $40 deduction. Upon selection of $200 withdrawal, $20 is dispensed and account balance is updated with $20 deduction. | 3 | Resolved | Normal | 0 | Fixed | 319544 | Jeff Roszell | Jan. 26, 2022 13:52 | 319540 | LAB1-Group30 | Jan. 27, 2022 20:09 | 0 | 0
3651676 | 68233 | ATM Project | 11 | ATM_1-11 | 292240 | Bug | 63979 | 1.1 | MFT - Incorrect deposit and withdrawal amounts during transfer. | System prints the amount transferred minus $0.50 from the total on the amount and also on the balance available Function: Customer is transferring money between two accounts Initial state: Customer selects an account and the amount of money to transfer. Steps to reproduce: Customer inserts card and pin number. Customer uses the first options menu to select the transfer option. Customer selects an existing From and To account, and then enters the amount they are transferring. Customer submits their transfer request. Expected outcome: All money requested, if available, is transferred to the selected account Actual outcome: $0.50 from the selected amount is not transferred into the new account. This amount remains in previous account after the transfer is complete. Ex. When transferring $20 from checking to savings, the money that's withdrawn from checking is less than $20 | 3 | Resolved | Normal | 0 | Fixed | 319544 | Jeff Roszell | Jan. 26, 2022 15:57 | 319540 | LAB1-Group30 | Jan. 27, 2022 20:08 | 0 | 0
3651671 | 68233 | ATM Project | 10 | ATM_1-10 | 292240 | Bug | 63979 | 1.1 | MFT - Incorrect card displayed on receipt | Function: Printed Receipt Initial State: System is servicing a customer, has performed a transaction and is printing a receipt Steps to reproduce the defect: Customer performs a transaction that warrants a receipt (eg. Balance Inquiry) Customer inserts card and pin number. Customer chooses a transaction type and presses 4 for balance inquiry. Customer then chooses checking account and waits for receipt to be printed. Expected outcome: The receipt should show the correct card number Actual outcome: Card number is 1 digit higher, eg. card 1 appears as card 2 on receipt and card 2 appears as card 3 on receipt | 2 | In Progress | Normal |  |  | 319544 | Jeff Roszell | Jan. 26, 2022 15:54 | 319540 | LAB1-Group30 | Jan. 27, 2022 20:07 | 0 | 0 | Jan. 26, 2022 22:58 Heidi Schaefer Defect still exists in version 1.1
3651669 | 68233 | ATM Project | 9 | ATM_1-9 | 292240 | Bug | 63979 | 1.1 | MFT - Incorrect balance upon deposit | Deposited amount shown on receipt is correct, but balance is updated with $10 less than what was deposited. Function: Deposit Initial State: Operator is turning the system on Steps to reproduce the defect: Customer inserts card and pin number. Customer uses the initial options menu to select the deposit screen. Customer deposits any amount of cash and finalizes the transaction. Customer then checks their receipt or performs a balance inquiry after using the options menu and selecting the deposit account. Expected outcome: Amount deposited is added to balance Actual outcome: $10 less than amount deposited is added to balance, can be negative if amount deposited is less than $10 | 2 | In Progress | Normal |  |  | 319544 | Jeff Roszell | Jan. 26, 2022 15:54 | 319540 | LAB1-Group30 | Jan. 27, 2022 20:06 | 0 | 0 | Jan. 26, 2022 22:54 Heidi Schaefer In version 1.1, $0.10 less than amount deposited is added to balance
3651680 | 68233 | ATM Project | 13 | ATM_1-13 | 292240 | Bug | 63979 | 1.1 | MFT - Duplicate non-functioning re-entry of pin screen. | Two separate screens ask for the PIN to be re-entered after the entry of an incorrect pin. First one has no effect. Function: PIN verification Initial state: Customer entering their PIN Steps to reproduce: Customer enters their card. Customer then enter the incorrect PIN, followed by the correct PIN Expected outcome: Customer is logged in after one correct PIN entry after an incorrect attempt Actual outcome: Customer must re-enter their PIN twice after incorrect attempt | 2 | In Progress | Normal |  |  | 319544 | Jeff Roszell | Jan. 26, 2022 16:00 | 319540 | LAB1-Group30 | Jan. 27, 2022 20:04 | 0 | 0 | Jan. 26, 2022 23:08 Heidi Schaefer Defect still exists in version 1.1
3652638 | 68233 | ATM Project | 41 | ATM_1-41 | 292240 | Bug | 63979 | 1.1 | MFT - $60 dollar option missing $ in withdrawal screens | Function: Withdrawing 60 dollars Initial state: System is displaying the withdraw selection screen Steps to reproduce: Customer inserts card and pin number. Customer uses the initial options menu to select the withdraw option. Customer then selects an available account and sees the withdrawal selection screen. Expected outcome: Customer should see "$60" Actual outcome: Customer sees "60" | 1 | Open | Normal |  |  | 319545 | Heidi Schaefer | Jan. 26, 2022 23:36 | 319540 | LAB1-Group30 | Jan. 27, 2022 20:04 | 0 | 0
3651848 | 68233 | ATM Project | 35 | ATM_1-35 | 292240 | Bug | 63979 | 1.1 | EXP - Upon transfer, from and to accounts are switched on receipt | Function: Printing receipt Initial State: System is servicing a customer, customer has just finished a transaction Steps to reproduce: Customer inserts card and pin number. Customer uses the options menu to navigate to the transfer screen. Customer enters a valid amount to transfer between two existing accounts, and a receipt is being printed. Expected outcome: The receipt has the correct "from" and "to" accounts, thereby displaying the correct transfer. Actual outcome: The receipt switches the account from which money is transferred with the one it is transferred into. Eg. when transferring from checking to savings, FROM: SVGS TO: CHKG appears on receipt. | 2 | In Progress | Normal |  |  | 319545 | Heidi Schaefer | Jan. 26, 2022 18:05 | 319540 | LAB1-Group30 | Jan. 27, 2022 20:03 | 0 | 0 | Jan. 26, 2022 19:54 Heidi Schaefer Defect still exists in version 1.1
3636981 | 68233 | ATM Project | 3 | ATM_1-3 | 292240 | Bug | 63979 | 1.1 | EXP - Unavailable bills - No warning | The system allows for login even when there are no available bills. Should at a minimum only allow deposits/balance inquiries. Function: Accessing withdrawal option Initial State: Customer has entered card and pin, is trying to access withdrawal option Steps to reproduce the defect: Customer enters pin and card. Customer uses the initial options menu to navigate to the withdraw screen and selects a valid account. Customer either tries to perform withdrawal after having access to the withdrawal option. Expected outcome: System does not let customer access the withdrawal option Actual outcome: Customer is able to access the option | 2 | In Progress | Normal |  |  | 319544 | Jeff Roszell | Jan. 20, 2022 12:42 | 319540 | LAB1-Group30 | Jan. 27, 2022 20:02 | 0 | 0 | Jan. 26, 2022 22:34 Heidi Schaefer Defect still exists in version 1.1
3651835 | 68233 | ATM Project | 34 | ATM_1-34 | 292240 | Bug | 63979 | 1.1 | EXP - Typo, terminal shows "wood" instead of "would" | Function: Terminal output Initial state: Transaction complete or cancelled Steps to reproduce: Customer inserts card and pin number. Customer uses the options menu to perform a deposit, withdrawal, transfer, or balance inquiry. Customer completes or cancels their transaction, and is asked if they would like to perform another Expected outcome: Customer sees "Would you like to do another transaction?" being displayed Actual outcome: Customer sees "Wood you like to do another transaction?" instead | 3 | Resolved | Normal | 0 | Fixed | 319545 | Heidi Schaefer | Jan. 26, 2022 17:59 | 319540 | LAB1-Group30 | Jan. 27, 2022 20:00 | 0 | 0
3651859 | 68233 | ATM Project | 36 | ATM_1-36 | 292240 | Bug | 63979 | 1.1 | EXP - Transfer amount is $0.50 less than requested | Function: Customer is transferring money between two accounts Initial state: Customer selects an account and the amount of money to transfer. Steps to reproduce: Customer inserts card and pin number. Customer navigates to the transfer screen using the initial options menu. Customer submits a transfer request from a valid account with adequate amount of money. Customer views the receipt or performs a balance inquiry by clicking option to continue their session and navigating to the balance inquiry screen. Expected outcome: All money requested, if available, is transferred to the selected account Actual outcome: $0.50 from the selected amount is not transferred into the new account. This amount remains in previous account after the transfer is complete. Ex. When transferring $20 from checking to savings, the money that's withdrawn from checking is less than $20 | 3 | Resolved | Normal | 0 | Fixed | 319545 | Heidi Schaefer | Jan. 26, 2022 18:10 | 319540 | LAB1-Group30 | Jan. 27, 2022 19:58 | 0 | 0
3651860 | 68233 | ATM Project | 37 | ATM_1-37 | 292240 | Bug | 63979 | 1.1 | EXP - No savings option on balance inquiry | Function: Viewing balance of savings account Initial state: System is servicing the customer Steps to reproduce: Customer inserts card and pin number. Customer selects to perform a balance inquiry using the option menu. Customer then is directed to the accounts they can view. Expected outcome: Customer is able to select an option for viewing their savings Actual outcome: Customer is not given this option | 3 | Resolved | Normal | 0 | Fixed | 319545 | Heidi Schaefer | Jan. 26, 2022 18:11 | 319540 | LAB1-Group30 | Jan. 27, 2022 19:55 | 0 | 0
3651786 | 68233 | ATM Project | 29 | ATM_1-29 | 292240 | Bug | 63979 | 1.1 | EXP - Incorrect dispensed amounts | Function: Withdrawing money as a customer Initial state: System is displaying multiples of 20 dollars for customer to withdraw Steps to reproduce: Customer inserts card and pin number. Customer navigates to the withdrawing screen and enters a valid amount of money to be withdrawn from a valid account. Expected outcome: Correct amount of cash is withdrawn from the account Actual outcome: Incorrect amount of cash is withdrawn. The receipt and balance are updated with amount that was dispensed. Eg. Upon selection of $20 withdrawal, $40 is dispensed and account balance is updated with $40 deduction. Upon selection of $200 withdrawal, $20 is dispensed and account balance is updated with $20 deduction. | 3 | Resolved | Normal | 0 | Fixed | 319545 | Heidi Schaefer | Jan. 26, 2022 17:35 | 319540 | LAB1-Group30 | Jan. 27, 2022 19:54 | 0 | 0
3651822 | 68233 | ATM Project | 32 | ATM_1-32 | 292240 | Bug | 63979 | 1.1 | EXP - Incorrect balance upon deposit | Function: Viewing balance following a deposit Initial state: System has performed a deposit and is waiting for customer to insert envelope Steps to reproduce: Customer inserts card and pin number. Customer navigates to deposit screen and enters the amount they are depositing. Customer inserts the envelope, then wait for receipt to be printed Expected outcome: Customer can view the correct amount of money, including that which was newly deposited, in their account Actual outcome: Balance updates with $0.10 less than deposited amount. This occurs upon deposit to the checking and savings account Ex. A $20 deposit is made to the checking account on account 1, but the total balance is $0.10 less | 2 | In Progress | Normal |  |  | 319545 | Heidi Schaefer | Jan. 26, 2022 17:54 | 319540 | LAB1-Group30 | Jan. 27, 2022 19:54 | 0 | 0 | Jan. 26, 2022 19:49 Heidi Schaefer Version 1.1 - Balance updates with $0.10 less than deposited amount.
3636962 | 68233 | ATM Project | 1 | ATM_1-1 | 292240 | Bug | 63979 | 1.1 | EXP - Empty log upon initial setup. | Upon setting the initial cash amount and turning on the system, nothing is represented in the log. Function: Logging of system Initial State: Operator is turning the system on Steps to reproduce the defect: System is OFF, operator clicks the ON button. Operator then enters the number of 20 dollar bills and turns on system. Finally, the operator views the log using the log button. Expected outcome: Start time is logged in the system Actual outcome: start time is not logged | 2 | In Progress | Normal |  |  | 319544 | Jeff Roszell | Jan. 20, 2022 12:28 | 319540 | LAB1-Group30 | Jan. 27, 2022 19:53 | 0 | 0 | Jan. 26, 2022 22:30 Heidi Schaefer Defect still exists in version 1.1
3636987 | 68233 | ATM Project | 4 | ATM_1-4 | 292240 | Bug | 63979 | 1.1 | EXP - Customers can access the log and previous transaction details | There should be a lock on the log files to the customers Function: accessing log files Initial State: system is servicing a customer Steps to reproduce the defect: Customer inserts card and pin number. Customer then clicks on the log button to view the logs. Expected outcome: customer is unable to view the previous log entries, especially those that are not from their own card. Actual outcome: customer is able to view previous log entries, including the card numbers of previous transactions and the amount they have recently withdrew. | 2 | In Progress | Normal |  |  | 319544 | Jeff Roszell | Jan. 20, 2022 12:50 | 319540 | LAB1-Group30 | Jan. 27, 2022 19:51 | 0 | 0 | Jan. 26, 2022 22:36 Heidi Schaefer Defect still exists in version 1.1
3636992 | 68233 | ATM Project | 6 | ATM_1-6 | 292240 | Bug | 63979 | 1.1 | EXP - Customer is able to clear the log | The customer can also clear the log from within their menu. This clearly shouldn't be able to occur. Function: Accessing the logs Initial State: System is ON Steps to reproduce the defect: Customer inserts card and pin number. Customer clicks on the Log button to view previous transaction logs. Customer is able to access these logs without inserting card/pin as well. From the log screen, customer then clicks on the clear button. Expected outcome: Customer is not able to clear previous logs. Actual outcome: Logs are cleared. | 2 | In Progress | Normal |  |  | 319544 | Jeff Roszell | Jan. 20, 2022 12:52 | 319540 | LAB1-Group30 | Jan. 27, 2022 19:48 | 0 | 0 | Jan. 26, 2022 22:37 Heidi Schaefer Defect still exists in version 1.1
3651790 | 68233 | ATM Project | 30 | ATM_1-30 | 292240 | Bug | 63979 | 1.1 | EXP - Cash dispensed when pressing unavailable options | Function: Using the system (general) Initial State: system is servicing a customer Steps to reproduce the defect: customer inserts card, adds pin, and navigates to a screen where some buttons do not correspond to an option on the screen. The customer then clicks on a button with no available options. For example, customer goes to withdraw screen and clicks on the number 9, which does not correspond to an option on the screen. Expected outcome: No changes to the system are made Actual outcome: System dispenses $20 and updates its log | 2 | In Progress | Normal |  |  | 319545 | Heidi Schaefer | Jan. 26, 2022 17:39 | 319540 | LAB1-Group30 | Jan. 27, 2022 19:46 | 0 | 0 | Jan. 26, 2022 19:46 Heidi Schaefer Defect still exists in version 1.1 | Jan. 26, 2022 21:25 Melanie Nguyen The transaction isn't recorded in the receipt but it's added to the log
3651831 | 68233 | ATM Project | 33 | ATM_1-33 | 292240 | Bug | 63979 | 1.1 | EXP - Card number appears to be 1 number higher on receipt | Function: Printed Receipt Initial State: system is servicing a customer, has performed a transaction and is printing a receipt Steps to reproduce the defect: Customer inserts card and pin number. Customer navigates through the options menu and performs a transaction that requires a receipt. This could include performing a balance inquiry or successfully withdrawing/transferring from/between an account. Expected outcome: The receipt should show the correct card number Actual outcome: Card number is 1 digit higher, eg. card 1 appears as card 2 on receipt | 2 | In Progress | Normal |  |  | 319545 | Heidi Schaefer | Jan. 26, 2022 17:58 | 319540 | LAB1-Group30 | Jan. 27, 2022 19:45 | 0 | 0 | Jan. 26, 2022 19:52 Heidi Schaefer Defect still exists in version 1.1
3652032 | 68233 | ATM Project | 40 | ATM_1-40 | 292240 | Bug | 63979 | 1.1 | EXP - Cannot turn ATM off once it's on, off button doesn't work | Function: Turning off the ATM Initial State: ATM is on Steps to reproduce: System is ON and cash has been inserted by an operator. Then, customer or operator clicks on the OFF button. Expected outcome: System shuts off with some confirmation message, log is updated. Actual outcome: System does not shut off | 3 | Resolved | Normal | 0 | Fixed | 319543 | Melanie Nguyen | Jan. 26, 2022 19:47 | 319540 | LAB1-Group30 | Jan. 27, 2022 19:43 | 0 | 0
3651866 | 68233 | ATM Project | 38 | ATM_1-38 | 292240 | Bug | 63979 | 1.1 | EXP - Balance inquiry for Money Market is invalid | Function: inquiring for Money Market as a customer Initial State: The system is servicing a customer, more specifically, the customer with card number 2. While card number 1 does not experience this error, we believe customers with other card numbers may still face this issue. Steps to Reproduce: Customer inserts card and pin number. Customer chooses to perform a balance inquiry and clicks on the option to see their existing Money Market account. Expected Outcome: Customer is able to view their balance in their money market account Actual Outcome: Customer is unable to access their money market account despite having one. | 3 | Resolved | Normal | 0 | Fixed | 319545 | Heidi Schaefer | Jan. 26, 2022 18:16 | 319540 | LAB1-Group30 | Jan. 27, 2022 19:41 | 0 | 0
3636974 | 68233 | ATM Project | 2 | ATM_1-2 | 292240 | Bug | 63979 | 1.1 | EXP - ATM Program Fully Locked - Insufficient Funds - Key Press | Function: withdrawing money from the system Initial State: System is servicing a customer Steps to reproduce: Customer inserts card and pin number. Customer navigates through the withdraw option to an existing account. Customer attempts to withdraw from an account with insufficient funds. Customer then hits the number 5. Expected outcome: Application does not respond, waits for customer to hit cancel Actual outcome: Application freezes! | 3 | Resolved | Normal | 0 | Fixed | 319544 | Jeff Roszell | Jan. 20, 2022 12:35 | 319540 | LAB1-Group30 | Jan. 27, 2022 19:39 | 0 | 0
3652015 | 68233 | ATM Project | 39 | ATM_1-39 | 292240 | Bug | 63979 | 1.1 | EXP - $60 withdrawal missing $ before 60 | Function: Withdrawing 60 dollars Initial state: System is on and displaying the withdraw selection screen Steps to reproduce: Customer inserts card and pin number, then selects withdraw option and an existing account. Expected outcome: Customer should see "$60" Actual outcome: Customer sees "60" | 1 | Open | Normal |  |  | 319545 | Heidi Schaefer | Jan. 26, 2022 19:37 | 319540 | LAB1-Group30 | Jan. 27, 2022 14:16 | 0 | 0